## ورقة1
Point | Priority | User | Est. Time | Notes
Remove RC portal and replace with department name, RC Portal should be removed from entire portal | High | All users
Redundunt Page name | High | All users |  | Check all pages
HR requests status show "Unkonwn" | High | All users |  | Review all requests and fix the status
It ticket create form : remove the assign to selector | High | All users |  | IT tickets should go to root user then gets assigned to IT employee
It tickets ref number must follow this format: TK-YYMM ticket count, EX: TK-2605001 | High | All users
Show employee name instead of "Account Emp" at top right | Low | All users |  | Show first last name
When creating a task to yourself it shouldn't go to line manager, it should be added to your list directly | High | All users
On Task create form: the assign to should show "Myself" and department names without employee names | Meduim | All users |  | as agreed on the tasks process, you assign tasks to another department not employee
At line manager on task assign to, the drop down should only show the names of the employees in that department only | High | All users
Notification page: add a link that takes the user to the desired action page | High | All users |  | Was available in the old system
Groups/committies menu link should not appear unless the user is a member of any group or comittiee | High | All users
In line manager menu, there is no communication link | High | All users |  | Line managers are considered as employees and they can raise a communication request
Task process error: when clicking on complete task then the task will change into canceled | High | All users
In tasks: the user must not change task status once the task is marked as completed | High | All users
In setting page: changing the theme not working | Low | All users
When creating a task from calendar page the form is not the same as the form in the tasks list page | Meduim | All users
Review Calendar functions | Low | All users
At root users page: the status must be "all status" as default status | Low | All users |  | Currently its "active users"
For the entire system: remove the need to escalate black box | High | All users |  | Remove it from everything
Admin requests ref number must follow this format: SS-YYMM ticket count, EX: GD-2605001 | High | All users |  | SS = the first 2 letters of the name of the request category, if the category name has more than one word then it will be the first letter of the first 2 words
At admin requests view page, show all related full log | Low | All users
At admin requests the destination user has no actions, the user must have an action to upload attachments and add comments on request completion | High | All users
At IT tickets page: remove the extra links : HR and admin requests | Low | All users |  | These located at top right of the page
at entire system in file attachment: excel file need to be allowed | Low | All users
Outbound communication give an error when sending the request with attachment | High | All users |  | we attached a word document
for all communications request show the request full details | Meduim | GM and liaison officer
Final dispatch not working | High | liaison officer
Add dashboard that contains summary about all communication | High | liaison officer |  | This requirement was sent in liaison officer process but its not completed
add communication link under support services | Low | liaison officer |  | Liaison officers are considered as employees and they can raise a communication request